RETINAH MEDIA GROUP · RMG DIGITAL

# ProDash+ — Single Source of Truth (SSOT)

Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Document owner & approver | Tinashe |  |  |
| Document owner & approver | Alvon |  |  |

Contents

LIFE 250ml Trader CRM, WhatsApp Bot & Branch Intelligence Platform
Client: ProDairy · Built and operated by: RMG Digital (Retinah Media Group)
Version 1.0 (Hybrid) · 27 September 2026 · Status: Draft for approval

# 0. Document Control

| Item | Value |
| --- | --- |
| Document | ProDash+ Single Source of Truth (SSOT), v1.0 Hybrid |
| Document owners and approvers | Tinashe · Alvon |
| Master copy | docs/ProDash_Plus_SSOT.md in the prodash-plus repository (the .docx is generated from it for signature) |
| Change rule | Any change to scope, definitions or dates is made in the master copy by pull request and approved by both owners |

## 0.1 Sources compiled

| Source | Short ref | Status after this document |
| --- | --- | --- |
| ProDairy 250ml SKU — GTM & System Rollout deck (10 slides) | Deck | Superseded, content absorbed |
| ProDash+ System Requirements & Design Specification v1.0 | Spec | Superseded, content absorbed |
| RMG Digital LIFE250 BRD & EDA / Problem Formulation Specification v0.1/0.2 | BRD | Superseded, content absorbed |
| RMG Digital LIFE250 Proposed Approach | — | Byte-identical duplicate of the BRD; retired |
| ProDash+ Task List (14-day, ~100 tasks) | Tasks | Re-mapped onto the Deck timeline (§14) |

## 0.2 Precedence rule

When sources disagree, this document records one decision (Appendix A). The tie-break order is:

| Topic | Wins |
| --- | --- |
| System flow, Phase 1 functionality, timelines, trader experience, segment names | Deck |
| Data contract, data quality, analytics definitions, CRM & consent, security, architecture | Spec |
| Long-range vision (multi-tenant, data worlds, data maturity L0–L3), hypotheses, TDSP / Data-Driven Scrum governance | BRD |
| Task breakdown and effort | Tasks, re-scheduled to Deck dates |

Owner decisions taken on 27 Sep 2026 and binding on this version:

- Trader identity is a system-issued trader code (primary key) plus a normalised cell number (unique contact attribute).

- WhatsApp runs on the WhatsApp Business Platform API (automated) in Phase 1.

- A two-way WhatsApp trader bot is a Phase 1 must-have.

- A Branch Manager interface (CSV drop + branch-level BI + branch operations) is a Phase 1 must-have.

## 0.3 Changelog

| Version | Date | Change |
| --- | --- | --- |
| 1.0 Hybrid | 27 Sep 2026 | First compiled SSOT from Deck, Spec, BRD and Tasks |

# 1. Purpose & North Star

ProDash+ exists to push LIFE 250ml sales through a trader CRM. It knows every trader who buys from a ProDairy shop, ranks them by value and risk, prompts them on WhatsApp on the right day with the right offer, tells branch staff who needs a personal touch, and measures whether it worked. [Spec §1, Deck s9]

The Deck's promise is the operating principle: "Every sale feeds the next sale." Transactions → Analytics → Insights → Action → Commercial growth, repeating every week. [Deck s9]

ProDash+ is also tenant one of RMG Digital's Marketing Intelligence Ecosystem: the warehouse, pipeline and governance are built once and reused for the next Retinah client. [BRD §1]

North-star metric — Incremental repeat revenue: repeat revenue from traders assigned to receive ProDash+ actions minus the repeat revenue expected from them, estimated from a persistent randomly held-out comparison group (intent-to-treat, §11.7). This is the headline number on the HQ dashboard once the sample is large enough to measure it.

Every feature serves one step of the loop below; a feature that serves none is out of scope. [Spec §2]

| Step | What ProDash+ does | Deck equivalent |
| --- | --- | --- |
| 1. Know | One profile per trader from every receipt, registration and WhatsApp interaction | Capture · Track |
| 2. Segment | Places every trader in a tier and flags those overdue against their own rhythm | Segment · Predict |
| 3. Prioritise | Ranks traders into trigger lists and a daily branch action queue | Score |
| 4. Act | WhatsApp bot prompts, offers and reorders; staff calls and visits for high-value traders | Prompt · Restock · Reward |
| 5. Measure | Did contacted traders buy again, versus the holdout group? | Log outcome — feeds next decision |

# 2. Phase 1 Scope

## 2.1 Test Day — 5 October 2026 (the Phase 1 acceptance gate)

A controlled pilot at selected ProDairy shops that validates the CRM engine end-to-end before rolling to all 16 shops. "Fail small, learn fast, scale confident." [Deck s2]

| # | Check | Pass condition on 5 Oct |
| --- | --- | --- |
| 01 | Trader capture | 20+ traders registered at pilot shops through counter + WhatsApp bot flows, each with a trader code and recorded opt-in |
| 02 | Order tagging | Every pilot-shop invoice that day carries a trader code and lands in the database |
| 03 | Data sync | Sales reach the CRM and dashboard within minutes for bot orders and counter capture; CSV drops processed on upload |
| 04 | RFM segment | Engine classifies all traders (6-month backfill + new registrations) into Champion / Regular / New / At-Risk / Lapsed |
| 05 | Trigger fire | First reorder prompt sent automatically via the WhatsApp bot on the right day to an opted-in trader, and the outcome logged |
| 06 | Dashboard live | ProDairy HQ and pilot Branch Managers log in, see live views, and log first actions |

PASS = system live and stable across all six checks → green-light rollout to all 16 shops. [Deck s2]

## 2.2 Phase 1 must-haves

| Capability | Section |
| --- | --- |
| WhatsApp trader bot (registration, opt-in, menu, one-tap reorder, tier, offers, human handover, automated prompts) | §9 |
| Branch Manager interface (CSV drop, branch-level BI, action queue, bot order confirmation, handover inbox) | §10 |
| HQ analytics dashboard (Deck slide 5 tiles + Spec screens) | §11 |
| Warehouse with 6-month CSV backfill, reconciled | §5, §13 |
| Segmentation, rhythm, lapse and priority engine | §6, §12 |
| Trigger & rules engine | §7 |
| Consent capture and enforcement | §12.8 |

## 2.3 In / out of Phase 1

| In Phase 1 (to 4 Nov) | Phase 1b — Promo activation (Nov–Dec) | Phase 2+ (Month 2 onwards) |
| --- | --- | --- |
| Everything in §2.2 | Loyalty points ledger and redemption | Stock-signal trigger (needs a stock feed) |
| SMS backup for traders without smartphones | Tuck-shop wraps, display equipment, giveaways | Demand forecasting per shop × SKU |
| Field-team task queue (high-value traders) | Referral rewards | ML lapse classifier replacing rules |
| Shop counter alert on trader arrival (flag in counter screen) | Prize draws | Branch-manager input app replacing CSV (§5.5) |
| Tier display in bot (points shown as 0 / "coming soon" until 1b) |  | Consumer, Household, Digital, Media, Competitor data worlds |
|  |  | Second Retinah tenant onboarding |

# 3. System Flow

One connected system across all 16 shops. Data flows from every trader touchpoint into a single intelligence layer and back out as actions. [Deck s3]

TRADER TOUCHPOINTS        DATA CAPTURE & CRM DB        INTELLIGENCE & RFM ENGINE     ACTION LAYER

------------------        ---------------------        -------------------------     ------------

Counter registration ─┐   Trader profile               Segment (R × F × M)           HQ analytics dashboard

WhatsApp bot          ├─► Every invoice tagged    ───► See — patterns & combos  ───► Branch Manager interface

QR code scan          │   SKU × cases × value × day    Predict — next order          Trigger & alert engine

Field team capture    │   Contact & catchment          Score — trader tier           WhatsApp bot messaging

Branch CSV drop ──────┘   Consent                                                    Field team task queue

▲                                                                                     │

└──────────────────────── outcome logged — feeds next decision ◄─────────────────────┘

## 3.1 Mapping to the warehouse layers [Spec §9]

| Deck stage | Implementation |
| --- | --- |
| Touchpoints | Branch Manager CSV drop (web), WhatsApp bot (webhook), counter registration screen (web), field-team form (web, mobile) |
| Data capture & CRM DB | bronze (raw, never edited) → silver (cleaned, typed, de-duplicated) → crm (registrations, consent, contacts, orders, messages) |
| Intelligence & RFM engine | gold (facts, dimensions, aggregates) + scoring (tiers, rhythm, lapse, priority, trigger lists) |
| Action layer | Next.js web app (HQ + Branch Manager), WhatsApp bot outbound sender, SMS backup, field task queue |

## 3.2 The retention & restocking loop [Deck s7]

ORDER → TRACK → PREDICT → PROMPT → RESTOCK → REWARD → (repeat)

| Stage | System behaviour |
| --- | --- |
| Order | Trader orders at the counter or in the bot |
| Track | Every line captured with trader code, SKU, cases, value, day |
| Predict | Engine estimates the next order date from the trader's personal rhythm |
| Prompt | Bot sends the reorder prompt on the usual order day |
| Restock | Order confirmed by the branch and fulfilled (collection or delivery) |
| Reward | Tier re-evaluated; perks credited (points from Phase 1b) |

Lapsed-trader recovery: DETECT (no order 14+ days or overdue against own rhythm, §7.2) → TRIGGER (recovery message) → OFFER (personalised perk) → REACTIVATE (back in the loop).

# 4. Identity Model

| Key | Rule |
| --- | --- |
| trader_code | Primary key. System-issued at registration (bot, counter, QR or field team), or auto-issued on CSV backfill. Format PD-<branch>-<6 digits>, printed on the trader's QR card and returned in the bot. |
| phone_e164 | Unique per client when present. Normalised to +2637XXXXXXXX (9 digits after 263, starting with 7). Invalid values go to a review list. Used to (a) match 6-month CSV history, (b) look up existing traders at registration to prevent duplicates, (c) WhatsApp and SMS delivery. |
| customer_id (internal) | Deterministic md5(client_id ‖ trader_code) — stable across every pipeline run, used by CRM tables. |

Rules:

- CSV backfill: receipts with a valid cell are grouped by phone_e164; each group gets one auto-issued trader code. The most frequent name spelling becomes the display name. [Spec §4.3]

- Registration: the bot and counter screen first look up the phone. If found, the existing trader code is confirmed and returned (history preserved); otherwise a new code is issued.

- Shared or family phones: one trader account; flagged when more than one distinct name appears frequently.

- Walk-ins with no cell and no code: counted in sales totals, excluded from customer analytics, tiers and queues. Never collapsed into an "anonymous customer".

- Traders without phones: may hold a trader code (QR card) with no phone. They count in analytics but can only be actioned in person or at the counter. [BRD §8]

- Live invoices: a trader code on every invoice from Test Day onward. [Deck s2]

# 5. Data Contract

The contract is binding for every source: branch CSV drops, the WhatsApp bot, counter capture and the future branch-manager input app. Switching a source changes only its loader, never the warehouse, analytics or dashboards. [Spec §4, §9.1]

## 5.1 Receipt / order fields

| Field | Required? | Format / example | Why it matters |
| --- | --- | --- | --- |
| receipt_no | Required | HFD-000123 | Groups line items; unique per (client, branch) |
| receipt_datetime | Required | 2026-04-17 10:42 | Recency, frequency, peak days and weeks |
| branch | Required | Highfield | Routes to the branch; must match ref.branches |
| trader_code | Required on live invoices from 5 Oct; optional on historical CSV | PD-HFD-000123 | Primary identity |
| customer_name | Required | Tendai Moyo | Display and matching support |
| customer_cell | Required* | 0772 123 456 / +263772123456 | Contact channel; history matching |
| product | Required | LIFE 250ml | Product mix, LIFE 250ml focus, bundles |
| quantity | Required | 12 | Volume |
| unit | Optional | case / unit | Converts to cases for the Deck's "cases" KPIs |
| unit_price | Required | 0.45 | Value, price checks |
| line_total | Required | 5.40 | Monetary score; reconciliation |
| currency | Required if both USD and ZiG occur | USD / ZiG | Mixed currencies are never summed |
| payment_method | Optional | Cash / EcoCash | Payment behaviour |
| customer_type | Optional | Tuckshop / musika / vendor / small shop / wholesaler / household | Playbooks by trader type [BRD §14.1] |
| fulfilment_type | Optional | collection / delivery | Restock loop [BRD §14.3] |
| source | System-set | csv / counter / whatsapp / field / app | Auditability |
| capture_level | System-set | L0–L3 | Data-quality weighting [BRD §5] |

*Receipts with neither a valid cell nor a trader code count towards sales totals but cannot enter the CRM. The share of receipts with an identified trader is a headline data-quality metric.

## 5.2 Accepted CSV shapes [Spec §4.2]

- Preferred: one row per line item (three products = three rows sharing a receipt_no).

- Accepted: one row per receipt with items packed into one column ("2x LIFE 250ml; 1x Yoghurt 500ml"). The loader splits it, and parse failures go to the reject file.

## 5.3 Data-quality handling [Spec §4.3 + review]

| Risk | Rule |
| --- | --- |
| Mixed cell formats | Normalise to +2637XXXXXXXX; invalid values go to a review list |
| Name spelling variants | Identity is trader code / phone; the most frequent spelling is displayed |
| Product name variants | Mapped through ref.product_map to a controlled product list maintained by RMG Digital |
| USD and ZiG mixed | Currency identified per line. Value KPIs are reported per currency, and a USD-equivalent is produced from ref.fx_rates (official daily rate). The rate source is recorded. |
| Same file uploaded twice | SHA-256 fingerprint; exact duplicates rejected automatically |
| Overlapping exports (e.g. Jan–Jun then Jun–Jul) | Receipt-level dedupe on (client, branch, receipt_no); latest load wins |
| Voids, refunds, negative quantities | Kept as signed lines linked to the original receipt where given; excluded from frequency counts |
| Line total ≠ quantity × unit price | Row flagged dq_reconciled = false; shown on Data Health |
| Wrong branch in a Branch Manager's file | Rows for other branches rejected (a Branch Manager can only load their own branch) |

## 5.4 Reconciliation

Revenue and receipt counts per branch per month must match independent totals supplied by ProDairy (finance or till end-of-day reports), not only the CSV's own sum. An upload whose totals disagree beyond an agreed tolerance is held from publishing. [Spec §8.1]

## 5.5 Future sources

When the branch-manager input app is ready, it writes the same contract to the same bronze table with source = app. CSV drop remains as a fallback. The app adds consent at point of sale and phone lookup at entry. [Spec §9.1]

# 6. Segmentation

## 6.1 Official Phase 1 tiers (Deck taxonomy)

| State | Type | Meaning | Trader-facing? | Perk ladder [Deck s7] |
| --- | --- | --- | --- | --- |
| New | Tier | First-time or early trader (first purchase ≤ 30 days ago and ≤ 2 purchases) | Yes | Welcome + first-order offer |
| Regular | Tier | Steady repeat buyer | Yes | Free delivery unlocked |
| Champion | Tier | Bulk / repeat champion — top R, F and M | Yes | Tuck-shop wrap + priority restocking |
| At-Risk | Engine state | Overdue against own rhythm or 14+ days without an order | No (tier kept for display) | Recovery message + personalised perk |
| Lapsed | Engine state | Gone quiet well beyond rhythm | No | Low-cost reactivation |

A trader's tier (New / Regular / Champion) is what they see in the bot. At-Risk and Lapsed are engine states that drive triggers and are shown internally only; the trader's last tier stays visible to them.

## 6.2 Scoring method [Spec §6.2, fixed]

| Measure | Definition | Score |
| --- | --- | --- |
| Recency (R) | Days since last purchase at the branch snapshot date | 1–5 by percentile within branch (5 = most recent) |
| Frequency (F) | Distinct purchase days in the last 180 days | Fixed thresholds: 1 → 1 · 2 → 2 · 3–4 → 3 · 5–8 → 4 · 9+ → 5 (recalibrated after data profiling) |
| Monetary (M) | Spend in the last 180 days, USD-equivalent | 1–5 by percentile within branch |

- Fixed F thresholds replace quintiles because most traders have one or two purchases and quintile cut points collide.

- Branches with fewer than 100 scored traders are pooled into one group for percentile scoring.

- Traders with fewer than 45 days of history are New and are not scored on F and M.

## 6.3 Analyst sub-segments (Spec's seven, complete grid)

Evaluated in this order; the first match wins. All 125 R × F × M cells map to exactly one sub-segment (verified by script).

| Order | Sub-segment | Rule | Maps to Deck state |
| --- | --- | --- | --- |
| 1 | Can't Lose | R 1–2, F 4–5, M 5 | At-Risk (top priority, personal call) |
| 2 | At Risk | R 1–2, F 3–5 | At-Risk |
| 3 | Lapsed | R 1–2, F 1–2 | Lapsed |
| 4 | Champions | R 4–5, F 4–5, M 4–5 | Champion |
| 5 | Loyal | R 3–5 & F 4–5, or R 4–5 & F 3 | Regular |
| 6 | Promising / New | R 4–5, F 1–2 | New if tenure ≤ 30 days, else Regular |
| 7 | Needs Attention | R 3, F 1–3 | Regular (reorder prompt priority) |

## 6.4 Final state assignment

- Lapsed if days since last order ≥ 3 × expected gap, or ≥ 90 days.

- Else At-Risk if the lapse trigger (§7.2) is met, or the sub-segment is Can't Lose / At Risk.

- Else New if first purchase ≤ 30 days ago and ≤ 2 purchases.

- Else Champion if the sub-segment is Champions.

- Else Regular.

Tier promotions and demotions are evaluated weekly (not daily) to avoid flip-flopping. A demotion needs two consecutive weekly evaluations. [BRD §18]

# 7. Trigger & Rules Engine

"The right nudge, the right day, the right trader." Every message is triggered by data, filtered by segment and delivered on WhatsApp — no bulk broadcasts. [Deck s6]

## 7.1 Trigger types

| Trigger | Fires when | Phase |
| --- | --- | --- |
| Time-based | The trader's usual order day approaches: predicted next order date = last order + expected gap, sent at the optimal time on that day (default 09:00) | 1 |
| Behaviour — lapse | Order pattern breaks (§7.2) | 1 |
| Behaviour — basket drop | Last basket value < 60% of the trader's trailing 90-day median basket (needs 3+ orders) | 1 |
| Event-based | New promo, prize draw or product launch, sent to eligible segments | 1 (promo content from 1b) |
| Segment move | Trader promoted to Regular or Champion (congratulation + perk), or demoted (gentle nudge) | 1 |
| Stock signal | Shop stock low → priority customers alerted | Phase 2 (no stock feed exists) |

## 7.2 Lapse rule (Deck + Spec hybrid)

- Expected gap = median days between the trader's purchase days, shrunk towards their segment median: gap = (n·own + 3·segment) / (n + 3), where n = number of gaps. With fewer than two gaps, the segment median is used.

- At-Risk trigger = no order for 14+ days (Deck) or days since last order > 1.5 × expected gap (minimum 7 days) (Spec), whichever comes first.

- Lapsed = > 3 × expected gap or > 90 days.

- The 14-day rule deliberately over-flags monthly buyers. This follows the BRD's stated preference for recall over precision in the pilot (lapse recall ≥ 0.7). The 14-day threshold is a configurable parameter, reviewed at the first weekly review after rollout.

## 7.3 Rules pipeline [Deck s6]

| Step | Action |
| --- | --- |
| 1 | Match trigger to trader segment |
| 2 | Select template for tone and context (English / Shona) |
| 3 | Personalise: name, tier, usual order |
| 4 | Add an offer or perk relevant to the tier |
| 5 | Schedule for the optimal send time |
| 6 | Log the outcome — feeds the next decision |

## 7.4 Guards applied before any send

- Consent = opted in (WhatsApp promotional messages).

- Not in the holdout group (§11.7). Holdout traders still receive transactional messages (order confirmations, replies).

- Contact cap respected (§8.3).

- Not already messaged for the same trigger in the cap window.

- Valid WhatsApp-reachable number, otherwise routed to SMS or the field queue.

## 7.5 Priority score (for the branch action queue and send order)

priority = monetary_score (1–5)

× min(overdue_ratio, 3)          -- overdue_ratio = days_since_last / expected_gap; only traders with ratio ≥ 1.0 are queued

× state_weight                   -- Can't Lose 1.5 | At-Risk 1.3 | Needs Attention 1.0 | others 0.7

Excluded: contacted within the cap window, opted out, holdout, no valid contact route.

From Phase 2 this becomes money at stake: expected spend per cycle × P(lapse), shown in currency.

# 8. Channels

## 8.1 Delivery channels [Deck s6]

| Channel | Role | Phase 1 implementation |
| --- | --- | --- |
| WhatsApp Business (API) | Primary — reorder, offers, prizes, bot | WhatsApp Business Platform (Cloud API directly or via a BSP) on a dedicated ProDairy number |
| SMS backup | Traders without smartphones | SMS gateway, same templates (short form), same guards |
| Field team task | High-value traders — in-person visit | Task list in the Branch Manager interface for Can't Lose / Champion traders |
| Shop counter alert | ProDairy staff prompted on the trader's arrival | Counter screen lookup by trader code/phone shows tier, due status and offer |

## 8.2 WhatsApp Business Platform rules

- A business-initiated message (reorder prompt, recovery, offer) must use a Meta-approved template and may go only to traders who have opted in.

- Free-form bot replies are allowed only inside the 24-hour customer service window opened by the trader's own message.

- Template categories: utility (order confirmations, reorder reminders) and marketing (offers, promos). Marketing templates are costlier and more restricted; reorder prompts are drafted as utility where Meta policy allows.

- The quality rating of the number is monitored; spikes in blocks or reports pause marketing sends.

## 8.3 Contact caps per state [Spec §7.1, Deck tiers]

| State | Action | Channel | Offer idea | Cap |
| --- | --- | --- | --- | --- |
| At-Risk — Can't Lose | Personal call from Branch Manager | Phone / field visit | Priority service / loyalty reward | 1 per 7 days |
| At-Risk | Recovery message + reorder reminder | WhatsApp bot | Small bundle incentive | 1 per 7 days |
| Regular — due today | Reorder prompt on usual day | WhatsApp bot | None or small add-on | 1 per 7 days (per order cycle) |
| New | Welcome + second-purchase prompt | WhatsApp bot | LIFE 250ml bundle intro / first-order incentive | 1 per 14 days |
| Champion / Regular | Recognition, basket growth | WhatsApp bot / in store | Tier perks, volume bundle | 1 per 30 days (promo) |
| Lapsed | Low-cost reactivation | WhatsApp bot | Come-back offer | 1 per 30 days |

Offers and budgets per state must be approved in writing by the ProDairy Sponsor before sending (Tasks T083).

# 9. WhatsApp Trader Bot (Phase 1 must-have)

"Traders don't download an app. Everything lives on WhatsApp Business — the tool they already use daily." [Deck s4]

## 9.1 Architecture

- The WhatsApp Business Platform sends inbound messages and status callbacks to a webhook (Supabase Edge Function). The webhook verifies the signature, stores the raw payload in bronze.wa_events, and writes to crm.wa_messages, crm.orders and crm.consent.

- A bot state machine (per trader conversation) drives menus and flows, using interactive list/button messages.

- An outbound sender reads the trigger list produced by the engine, applies the §7.4 guards, sends templates and records delivery, read and reply statuses as outcomes.

## 9.2 Flows

A. Onboarding & registration (trader messages the ProDairy number, taps a click-to-chat link, or scans the shop QR)

- Greeting and a short data/consent notice (English / Shona), with a link to the privacy notice.

- Opt-in question: "May ProDairy send you order reminders and offers on WhatsApp?" Yes → opted_in; No → opted_out (the bot still serves requests the trader starts).

- Phone lookup: an existing trader from CSV history is linked and their trader code confirmed; otherwise the bot captures name, business name, outlet type, home branch (list) and area/catchment.

- Issues the trader code and sends a digital card with a QR code (shown at the counter to tag invoices).

- Welcome message + first-order offer (New tier).

B. Main menu [Deck s4]

| Menu item | What the trader sees / does |
| --- | --- |
| Greeting | "Hi Baba T — your ProDairy dashboard 👇 TIER: Regular • Loyalty: 45 pts" (points live from Phase 1b; until then tier only) |
| Reorder | One-tap "Reorder your usual? (12 cases)". The usual order is derived from history (modal basket). Options: Yes · Change quantity · Cancel; then choose collection or delivery and day. |
| My tier | Current tier, progress to the next tier, unlocked perks |
| Offers | Perks matched to the trader's state — no generic broadcast |
| Support | Human handover to the shop team. The conversation appears in the Branch Manager handover inbox; the bot pauses until staff close it. Never a dead end. |
| Stop | "STOP" at any time sets opted_out across all branches, confirmed within 24 hours [Spec §11] |

C. Bot order lifecycle

requested (trader confirms in bot) → confirmed (Branch Manager confirms stock and day in the Branch Manager interface) → fulfilled (collected or delivered; becomes an invoice with the trader code) or cancelled. The trader receives a message at each step ("Confirmed ✓ Delivery Fri AM"). Bot orders enter the warehouse with source = whatsapp. Revenue is counted when fulfilled, never when requested.

D. Automated prompts: time-based, lapse, basket-drop, segment-move and event triggers (§7) sent as approved templates with quick-reply buttons ("Yes reorder", "Not now", "Talk to shop").

## 9.3 Languages

English and Shona templates and menus at launch; Ndebele added as needed. [BRD §7]

## 9.4 Prerequisites and deadlines (critical path for 5 Oct)

| Prerequisite | Owner | Deadline |
| --- | --- | --- |
| Choose Cloud API direct vs BSP | RMG Project Lead | Mon 28 Sep |
| Meta Business Manager verification for ProDairy (legal name, documents) | ProDairy Sponsor + RMG Project Lead | Submit Mon 28 Sep |
| Dedicated WhatsApp number not already registered on the WhatsApp app | ProDairy Sponsor | Mon 28 Sep |
| Display name approval | RMG Project Lead | Tue 29 Sep |
| Templates submitted (welcome, reorder prompt, recovery, order confirmation, tier promotion — EN + SN) | RMG Project Lead + Data Analyst | Tue 29 Sep |
| Consent / privacy wording approved by ProDairy | ProDairy Sponsor | Tue 29 Sep |

Test-day fallback: if verification or templates are not approved by Fri 2 Oct, Test Day runs on the Meta test number, which can message up to five pre-registered recipient numbers (pilot traders and staff). The system flow is identical; only the sender number changes. Production-number go-live then moves into the Iterate window (6–19 Oct).

## 9.5 Value exchange [Deck s8]

| Trader gives | Trader gets |
| --- | --- |
| Registration + contact details | Tiered discounts & volume rebates |
| Regular purchase & standing orders | Free delivery (tier-unlocked) |
| Order data (SKU, cases, day, value) | Priority restocking |
| Feedback on offers and stock | Full tuck-shop wrap (top performers) |
| Referrals to other traders | Display equipment & print material |
| Loyalty to the ProDairy brand | Giveaway stock, trader promos, referral rewards & recognition |

Tier progression: More orders → higher tier → bigger rewards. New (welcome + first-order offer) → Regular (steady weekly buyer, free delivery unlocked) → Champion (bulk/repeat, tuck-shop wrap + priority). [Deck s7]

## 9.6 Bot acceptance criteria

- A new trader can register, opt in and receive a trader code in under 2 minutes.

- An existing CSV-history trader registering by phone is linked, not duplicated.

- One-tap reorder creates a requested order visible to the right Branch Manager within 1 minute.

- STOP sets opt-out across all branches; no promotional message follows.

- Support hands over to a human; the conversation is visible in the branch inbox.

- An automated reorder prompt fires on the predicted day to an opted-in, non-holdout trader, and the outcome is logged.

# 10. Branch Manager Interface (Phase 1 must-have)

A mobile-first web interface for each of the 16 Branch Managers. Every view is restricted to the manager's own branch by row-level security.

## 10.1 CSV drop

- Drag-and-drop (or tap to choose) a CSV.

- Instant in-browser check before upload: headers against the data contract, a 20-row preview, a count of rows with invalid cell numbers, and unknown products and branches.

- Upload goes direct to private storage (signed upload URL). The file is fingerprinted, an exact duplicate is rejected with a clear message, and the pipeline runs (load → clean → dedupe → reconcile → score).

- Upload history: file, time, status (processing / published / held / rejected), rows loaded, rows rejected, reconciliation result. The reject file is downloadable with a reason per row.

- Only the manager's own branch's rows are accepted; rows for other branches are rejected.

## 10.2 Branch BI (own branch only)

| View | Content |
| --- | --- |
| KPI tiles | Registered traders (+ this week), weekly 250ml cases, revenue (per currency + USD-eq), reorder rate (trailing 4 weeks), At-Risk traders, revenue at risk |
| Segment mix | Champion / Regular / New / At-Risk / Lapsed counts and revenue, plus month-to-month movement |
| Peak days & weeks | Revenue and orders by weekday and ISO week |
| Product mix | LIFE 250ml share of revenue and traders; products most often bought with LIFE 250ml (bundle candidates) |
| Top traders | Pareto — share of revenue from the top 20% of the branch's traders |
| Branch vs network | The branch's KPIs against the all-branch average (no other branch's detail shown) |
| Data stamp | "Data current to [date]" and the last upload status on every view |

## 10.3 Branch operations

| Screen | Purpose |
| --- | --- |
| Action Queue | Today's ranked list (§7.5): trader, tier/state, why they're listed, suggested message and offer, tap-to-call and WhatsApp link; one-tap outcome logging (reached / no answer / will order / not interested / wrong number / opted out) in under 10 seconds |
| Bot orders | Pending WhatsApp orders to confirm, reschedule or cancel; the confirmation goes back to the trader automatically |
| Handover inbox | Conversations the bot handed to a human; reply within the 24-hour window |
| Trader 360 | One trader's purchases, products, rhythm, tier history, messages, contacts, orders and consent |
| Registrations | New traders this week (bot / counter / QR / field); counter registration form |
| Field tasks | High-value traders to visit; visit outcome logging |

## 10.4 Branch Manager acceptance criteria

- A manager uploads their branch CSV from a phone and sees rows loaded, rejected and reconciled within 5 minutes.

- A second upload of the same file is rejected, and a malformed file gives a clear, row-level error.

- A manager cannot see, via the UI or direct API calls, any other branch's traders or numbers.

- The Action Queue, bot orders and handover inbox work on a mid-range Android over mobile data.

# 11. HQ Analytics Dashboard & Accuracy Standards

"The back-end where growth decisions get made." [Deck s5]

## 11.1 HQ Overview (Deck slide 5)

| Element | Content |
| --- | --- |
| Header | "PRODAIRY 250ml • TRADER CRM DASHBOARD" · Live · All 16 Shops · Today · branch filter |
| KPI tiles | Registered traders (+ this week) · Weekly volume (cases 250ml) · Reorder rate (trailing 4 weeks) · At-risk traders (needs recovery) |
| RFM segments | Share of traders: Champions / Regulars / At-Risk / New (+ Lapsed) |
| Shop performance | Top 5 shops by weekly volume (all 16 on drill-down) |
| Actions today | At-risk traders with recovery WhatsApp queued · traders due today (reorder prompt firing at 09:00) · traders promoted to Champion (tier reward) · new registrations (welcome flow) |
| Money | Revenue, revenue at risk, and incremental repeat revenue (shown once the holdout comparison has enough data, §11.7) |

The Deck's "live" means bot orders, registrations and message outcomes update within minutes; CSV-based sales update when each branch uploads. Tier distribution is recomputed nightly. [Deck s5]

## 11.2 Further HQ screens [Spec §8]

| Screen | Answers | Drives |
| --- | --- | --- |
| Segments | Traders and revenue per state, and monthly shifts | Which states need campaigns |
| Sales Trends | Peak weeks/days, product mix, basket pairings, branch comparison | Campaign timing, bundles, staffing |
| Action Results | Messages, contacts, response and repurchase rates by state and branch; lift vs holdout | Which playbooks to keep, change or stop |
| Trader 360 | As §10.3, all branches | Account management |
| Data Health (RMG) | Last upload per branch, rows loaded/rejected, % identified traders, reconciliation, WhatsApp quality rating, template status | Whether the numbers can be trusted today |

## 11.3 Accuracy standards [Spec §8.1]

- Every KPI has one written definition in docs/data_dictionary.md, used on every screen.

- Revenue reconciles to ProDairy's independent totals before an upload is published.

- Every screen shows "data current to [date]" and the branch filter in use.

- Groups with fewer than 20 traders show counts, not percentages.

## 11.4 KPI definitions

| KPI | Definition |
| --- | --- |
| Registered traders | Traders with a trader code and at least one registration or purchase event |
| Weekly volume | Sum of LIFE 250ml quantity converted to cases, ISO week |
| Reorder rate (trailing 4 weeks) | Of traders who purchased in weeks −8 to −5, the share who purchased again in weeks −4 to −1 |
| Revenue at risk | Typical monthly spend (trailing 180-day spend ÷ 6) of At-Risk traders, including Can't Lose |
| Repeat purchase rate | Share of traders active in the month who also bought in the prior month |
| Incremental repeat revenue | §11.7 |

## 11.5 Snapshot rule

Recency for each branch uses that branch's latest loaded receipt date as "today", not the calendar date. This prevents a late upload from making a whole branch look lapsed. Branches whose data is older than their expected upload cadence are flagged on Data Health. For WhatsApp-bot and counter data (live), the calendar date is used. [Spec §6.1, fixed]

## 11.6 What six months of history supports [Spec §5]

| Analysis | Supported? |
| --- | --- |
| Segmentation | Yes |
| Personal rhythm & lapse | Yes for traders with 3+ purchases; others use the shrunk segment rhythm |
| Peak weeks/days, month-end effects | Yes |
| Cohort retention | Partially (earliest cohorts ~5 months) |
| Basket / co-purchase | Yes |
| Lifetime value | Indicative range only |
| Annual seasonality, long-range forecasts | No — revisit in 2027 |
| Out-of-stock risk | No — needs a stock feed (Phase 2) |

## 11.7 Proving it works — holdout group

- Persistent assignment: each eligible trader is assigned once, hash(customer_id, experiment_salt) < 0.20 → holdout, and stored in crm.experiment_assignment. The assignment never changes during the evaluation period.

- Scope: At-Risk (excluding Can't Lose) and Regular traders due a reorder prompt. Holdout traders receive no promotional prompts but still get transactional service and can use the bot.

- Measure (intent-to-treat): repurchase within max(14 days, 1.5 × expected gap) for everyone assigned to treatment vs everyone assigned to holdout, whether or not a message was delivered or answered.

- Reporting: lift is shown with a 90% confidence interval and hidden until at least 400 traders per arm have been evaluated.

Sample size needed (two-sided α = 0.05, power 0.8, detecting a 30% → 35% repurchase lift):

| Holdout share | Total eligible traders | Holdout traders |
| --- | --- | --- |
| 10% | ≈ 7,400 | ≈ 740 |
| 20% (chosen) | ≈ 4,200 | ≈ 840 |
| 50% | ≈ 2,750 | ≈ 1,370 |

Evaluations are pooled across weeks, so the required totals accumulate over the pilot rather than needing to exist on day one.

# 12. Analytics Engine, Consent & Data Protection

## 12.1 Engine outputs (written after every load and nightly)

| Output | Content |
| --- | --- |
| scoring.trader_scores | Append-only per run: snapshot date, R/F/M scores, sub-segment, state, tier, expected gap, overdue ratio, priority |
| scoring.trigger_list | Trader × trigger × scheduled send time, after guards |
| gold.rpt_action_queue | Frozen daily queue per branch (rank, reason, message, offer) |
| crm.queue_exposure | What was shown or sent to whom, and when — the basis of every outcome measurement |

## 12.2 Supporting analyses [Spec §6.5]

Pareto (top 20% revenue share), peak weeks/days, product mix and LIFE 250ml bundle pairings, cohort retention.

## 12.3 Models roadmap [BRD §17, §18]

| Model | Phase 1 | Phase 2+ | Success metric |
| --- | --- | --- | --- |
| Lapse | Rules (§7.2) | Classifier (scikit-learn) / BG/NBD P(alive) (pymc-marketing), adopted only if it beats the rules | Recall ≥ 0.7 on verified lapses |
| Segmentation | Rules (§6) | Clustering review | No tier flip-flopping week to week |
| Demand forecast | — | Shop × SKU weekly forecast | MAPE target set after 8+ weeks |
| Campaign impact | Holdout lift (§11.7) | Multi-channel attribution | CI excludes zero |

## 12.4 Working hypotheses (analytics backlog) [BRD §12]

| # | Hypothesis |
| --- | --- |
| H1 | Traders who opt into the WhatsApp bot reorder more often than captured-but-not-engaged traders |
| H2 | Shops sending structured reorder-day reminders show lower lapse rates than walk-in reliance |
| H3 | Informal-market price premium correlates with stock-out frequency (needs price and stock data — Phase 2) |
| H4 | A small group of heavy traders drives a disproportionate share of 250ml sell-out |
| H5 | Outlets closer to the collection/delivery point reorder more frequently |
| H6 | Manual (L0) capture has higher missing and duplicate rates than bot/QR (L1) capture |

## 12.5 Data maturity ladder [BRD §5]

| Level | Capture | ProDash+ Phase 1 position |
| --- | --- | --- |
| L0 Manual | Counter register, end-of-day entry | Branch CSV drop of historical and ongoing receipts |
| L1 Structured | QR registration, dedicated WhatsApp number, unique codes | Phase 1 target: trader codes + WhatsApp bot |
| L2 Lightweight automation | Mobile/PWA app per branch, POS/invoice tagging | Branch-manager input app (Month 2–3) |
| L3 Full automation | WhatsApp API webhook, POS API / OCR | Bot already on the API; POS feeds Month 4+ |

## 12.6 Data quality targets [BRD §18, Spec §11]

| Measure | Target |
| --- | --- |
| Receipts with an identified trader (code or valid cell) | ≥ 80% historical; ≥ 90% by 19 Oct; ≥ 97% by 4 Nov on live invoices |
| Unreconciled uploads published | 0 |

## 12.7 Governance of definitions

Every threshold (14 days, 1.5×, 3×, 90 days, F cut-offs, weights, holdout share) lives in one parameter table ref.engine_params, versioned, and changes only by owner approval.

## 12.8 Consent & data protection [Spec §7.3, BRD §5]

- Zimbabwe Cyber and Data Protection Act (2021) applies.

- Every historical number is consent unknown. No promotional WhatsApp or SMS is sent to unknown or opted-out numbers.

- Historical traders are invited to opt in through a branch relationship contact (call or counter) or by messaging the bot themselves. Their first business-initiated message waits until they have opted in.

- Opt-in is captured explicitly at bot or counter registration (so Test Day traders are messageable).

- Opt-out is permanent across all branches and honoured within 24 hours; STOP in the bot works at any time.

- Customer data never enters the repository; raw files are kept in private storage only.

- Open legal items: cross-border hosting of personal data (the database region is outside Zimbabwe) and data-controller registration with POTRAZ — to be confirmed by ProDairy/RMG counsel before rollout (§18).

# 13. Architecture & Stack

| Layer | Implementation | Notes |
| --- | --- | --- |
| Web app | Next.js (App Router, TypeScript), mobile-first; HQ + Branch Manager + RMG admin | Hosted on Vercel (or RMG VPS); dev and prod |
| Auth | Supabase Auth, invite-only (sign-ups off), magic link / phone OTP; role, client and branch in token claims | Roles: HQ decision maker, Branch Manager, RMG admin |
| Database | Supabase Postgres, schemas bronze, silver, gold, scoring, crm, ops, ref, api | client_id on every row (multi-tenant ready) [BRD §7] |
| Security | Row-level security on every crm/ops/ref table; the app reads only the api schema (views and functions filtered by allowed branches) | bronze/silver/gold are not exposed to the API |
| Uploads | Browser → signed upload URL → private bucket raw-uploads; ops.load_log row per file (SHA-256 unique) | Avoids serverless body-size limits |
| Pipeline worker | Picks up pending loads: loader → dbt build (silver/gold + tests) → scoring → publish only if all tests pass | GitHub Actions (repository dispatch) or a worker on the RMG VPS |
| Transformations | dbt (silver, gold); segmentation, rhythm, lapse and priority in dbt SQL for Phase 1; Python for Phase 2 models | dbt connects via the Supabase session pooler |
| WhatsApp | Edge Function webhook (verify signature → bronze.wa_events, crm.*); outbound sender job | Templates and quality rating shown on Data Health |
| SMS | SMS gateway API, same guard logic | Backup channel |
| Internal BI | Metabase, read-only on gold, RMG only | Analyst QA |
| Environments | Supabase prodash-dev and prodash-prod; migrations under supabase/migrations; CI runs lint, dbt build and tests on every pull request | Secrets in a password manager and repository secrets only |

Key design rules

- dbt owns silver and gold. Scoring writes to scoring. CRM data is written only by the app, the bot and the webhook. No foreign keys point from crm tables to dbt-rebuilt tables.

- Keys are deterministic hashes, never row numbers.

- Tier history, queues and message exposures are append-only, so any past screen or result can be reproduced.

# 14. Timeline (Deck-led)

"Nine days to test day. Four weeks to all 16 shops live. Twelve weeks to trader promo full activation." [Deck s10]

| Window | Dates | Deck goal | ProDash+ deliverables |
| --- | --- | --- | --- |
| T-9 → T-0 Build & Prep | 26 Sep – 4 Oct | System readied, pilot shops briefed, first traders contacted | See §14.1 |
| Test Day | Mon 5 Oct | Six checks executed at pilot shops; green-light for scale | §2.1 |
| T+1 → T+14 Iterate | 6 – 19 Oct | Fixes applied, field team briefing, collateral distributed | Production WhatsApp number live (if on test number); bot order lifecycle and handover inbox hardened; remaining Branch BI views; Action Results screen; holdout running; KPI accuracy check; security test; UAT |
| T+15 → T+30 16-Shop Rollout | 20 Oct – 4 Nov | System live across every ProDairy shop; first reports out | All 16 Branch Manager accounts and training; weekly CSV drop routine; QR cards at every counter; first weekly results report |
| T+30 → T+90 Promo Activation | Nov – Dec | Trader promo live, perks awarded, first tuck-shop wraps | Loyalty points ledger, perk redemption, referral rewards, prize draws (Phase 1b) |
| Automate & Expand | Month 2–3 | — | Branch-manager input app (L2); POS/invoice tagging; daily ETL; Consumer & Household data worlds [BRD §4] |
| Multi-tenant Scale | Month 4+ | — | Second Retinah client; predictive scoring; real-time risk alerts [BRD §4] |

## 14.1 Build & Prep critical path (to Test Day)

| Date | Data Engineer | Data Analyst | Full-stack Dev | Project Lead |
| --- | --- | --- | --- | --- |
| Sat 26 – Sun 27 Sep | Supabase dev/prod projects, schemas, ops.load_log, storage bucket | Profiling plan; SSOT sign-off | Next.js scaffold, auth, app shell | SSOT approval; Meta/BSP decision; CSV confirmed received |
| Mon 28 Sep | Loader + bronze; load 6-month CSV | Data profile (coverage, currency, products, totals) | WhatsApp webhook + test number; bot state machine skeleton | Submit Meta verification, number, display name; book pilot shops |
| Tue 29 Sep | silver: cleaning, phone normalisation, dedupe, trader codes | Product map, currency rule, reconciliation vs ProDairy totals | Bot registration + opt-in + trader code flow | Submit templates (EN/SN); consent wording approved |
| Wed 30 Sep | gold: facts, dimensions; RLS + api views | Segmentation + rhythm + lapse + priority in dbt | Branch Manager CSV drop + upload history | Draft playbooks and offers |
| Thu 1 Oct | Pipeline worker (upload → dbt → scoring → publish) | Trigger list + guards; holdout assignment | Bot menu: Reorder, My tier, Offers, Support; bot orders screen | Sponsor approves offers and budgets |
| Fri 2 Oct | Outbound sender (templates, statuses) | Branch BI v1 datasets; HQ tile datasets | Branch BI v1 (KPI tiles + segment mix); HQ Overview tiles; Action Queue + logging | Template status check → decide test number vs production number |
| Sat 3 Oct | Security test (branch isolation, direct API) | Top-50 queue review with pilot Branch Managers | Handover inbox; mobile test | Pilot shop briefing; QR cards printed |
| Sun 4 Oct | Deploy to prod; load and reconcile | KPI spot-check vs CSV | Prod deploy; accounts created | Go/no-go for Test Day |
| Mon 5 Oct | Test Day — six checks |  |  |  |

The kickoff dates in the Task List (Day 1 = 28 Sep, Day 12 go-live = 9 Oct) are superseded by this schedule. Task List items are re-mapped as follows:

| Task List phase | IDs | Window |
| --- | --- | --- |
| 0–1 Pre-kickoff, environment | T001–T018 | 26–27 Sep |
| 2–3 Ingestion, profiling, data contract (agreed by email; signature by 19 Oct) | T020–T037 | 28–29 Sep |
| 4 Silver | T040–T049 | 29 Sep |
| 5 CRM data & security | T050–T053 | 30 Sep – 3 Oct |
| 6 Gold & engine | T060–T075 | 30 Sep – 1 Oct (T075 data dictionary by 19 Oct) |
| 7 Validation & playbooks | T080–T085 | 1–3 Oct |
| 8 Web app build (+ bot, Branch Manager interface — new) | T090–T101 | 27 Sep – 4 Oct |
| 9 QA | T110–T115 | 3–4 Oct (core), full pass 6–19 Oct |
| 10 Production deployment | T120–T128 | 4 Oct (pilot), full UAT 6–19 Oct |
| 11 Go-live, training | T130–T132 | 5 Oct pilot; 20 Oct – 4 Nov all shops |
| 12 Hypercare & handover | T140–T145 | 6–19 Oct |

Test-day minimum if the plan slips: checks 01, 02, 04 and 06 on the production stack, plus checks 03 and 05 on the Meta test number. Never cut: revenue reconciliation, branch-level access control, consent enforcement, outcome logging. [Tasks Read Me]

# 15. Success Metrics & Gates

| Gate / measure | Target | Source |
| --- | --- | --- |
| System pass on 5 Oct | All six checks pass | Deck s10 |
| All 16 shops live | By 4 Nov (T+30) | Deck s10 |
| Traders registered | 300+ by 4 Dec (T+60) | Deck s10, BRD §3 |
| Reorder rate | Lifted vs baseline measured in Build & Prep | Deck s10 |
| First Champions promoted | During rollout | Deck s10 |
| Receipts with an identified trader | ≥ 80% historical; ≥ 97% on live invoices by 4 Nov | Spec §11, BRD §18 |
| Queue actioned | ≥ 70% of queued traders actioned each week | Spec §11 |
| Bot reorder-prompt response rate | ≥ 20% | BRD §3 |
| Reactivation of At-Risk traders | Treated group repurchases more than holdout (CI excludes zero once powered) | Spec §11 |
| Opt-ins | Growing monthly; opt-outs honoured within 24 hours | Spec §11 |
| Dashboard accuracy | Zero unreconciled uploads published | Spec §11 |
| Lapse rule | Recall ≥ 0.7 on verified lapses | BRD §18 |
| Platform reuse | Second tenant onboarded with ≤ 25% of tenant-one effort | BRD §3 |

# 16. Governance & Delivery Method

Delivery uses Microsoft TDSP for lifecycle gates and artefacts and Data-Driven Scrum for the hypothesis-led weekly cadence. [BRD §4, §19]

| TDSP phase | Exit artefact | Window |
| --- | --- | --- |
| Business Understanding | This SSOT (approved) | 27 Sep |
| Data Acquisition & Understanding | Data profile report; data contract agreed | 29 Sep |
| Modelling | Engine report: tiers, rhythm, lapse, priority, holdout | 1 Oct |
| Deployment | Test Day pass; deployment note | 5 Oct |
| Customer Acceptance | Rollout exit report against §15 | 4 Nov |

Lanes: Data Engineering · Analytics/EDA · Modelling · BI/Delivery (incl. bot). Daily 15-minute stand-up and evening demo during Build & Prep; weekly review ("what did the data tell us?") from 12 Oct.

| Role | Accountable for |
| --- | --- |
| ProDairy Sponsor | Business sign-off, consent language, offers and budgets, Meta verification documents, independent revenue totals, final acceptance |
| RMG Project Lead | Programme priorities, TDSP gates, client coordination, WhatsApp onboarding |
| Data Engineer | Warehouse, pipeline, security, webhook and sender |
| Data Analyst | Profiling, reconciliation, engine, KPI definitions, data dictionary |
| Full-stack Developer | Next.js app, Branch Manager interface, bot flows |
| Branch Managers | CSV drops, queue work, bot order confirmation, handovers |

# 17. Risks & Mitigations

| Risk | Mitigation |
| --- | --- |
| Meta verification or template approval not ready by 5 Oct | Submit on 28–29 Sep; Test Day on the Meta test number (§9.4) |
| Test-day scope too large for 8 days | Critical path §14.1; test-day minimum defined; "Should" items deferred to Iterate |
| Low identified-trader coverage in the historical CSV | Measured on 28 Sep; if < 60%, lean on bot/counter registration and QR cards |
| Messaging without consent (law, trust, WhatsApp number quality) | Consent guard (§7.4); opt-in at registration; STOP everywhere; quality rating monitored |
| Branch staff do not log contacts or confirm bot orders | 10-second logging, today's top traders only, pending-order alerts, weekly branch results |
| Branch Managers upload wrong or partial files | In-browser contract check, own-branch rows only, overlap dedupe, reconciliation hold |
| Credit claimed for sales that would have happened anyway | Persistent holdout, intent-to-treat, confidence intervals (§11.7) |
| Holdout too small to show lift | 20% holdout, pooled weeks, lift hidden until powered |
| 14-day lapse rule over-flags monthly buyers | Accepted for recall; parameter reviewed at first weekly review |
| Mixed USD/ZiG values | Per-currency reporting + USD-equivalent from an official rate table |
| Cross-border hosting of personal data / POTRAZ registration | Legal confirmation before rollout (§18) |
| Informal traders without stable phones | Trader code on QR card works without a phone |
| Scope creep toward the full data-world vision | Phase gates in §2.3 and §14 |

# 18. Open Questions & Decisions Log

| # | Question | Owner | Needed by |
| --- | --- | --- | --- |
| 1 | Has the full six-month CSV been received? One file for all branches or one per branch? Which branches? | ProDairy Sponsor | 27 Sep |
| 2 | Are values in USD, ZiG or both, and is there a currency column? | ProDairy Sponsor | 28 Sep |
| 3 | Independent monthly revenue totals per branch for reconciliation | ProDairy Sponsor | 29 Sep |
| 4 | Cloud API direct or BSP? Which dedicated number? Who holds the Meta Business Manager? | RMG Project Lead / ProDairy | 28 Sep |
| 5 | Consent and privacy wording (ProDairy's or Retinah's template) | ProDairy Sponsor | 29 Sep |
| 6 | Which shops are the Test Day pilot shops, and who at each works the queue and bot orders? | ProDairy Sponsor | 29 Sep |
| 7 | Approved offers and budgets per state; delivery rules for free delivery | ProDairy Sponsor | 1 Oct |
| 8 | Are invoices issued from a till/POS or by hand at pilot shops (how the trader code is attached)? | ProDairy Sponsor | 29 Sep |
| 9 | Cross-border data hosting and POTRAZ registration | Counsel | 19 Oct |
| 10 | SMS gateway provider | RMG Project Lead | 19 Oct |
| 11 | Expected launch date of the branch-manager input app | ProDairy | 4 Nov |
| 12 | Unit-to-case conversion for LIFE 250ml | ProDairy | 29 Sep |

# Appendix A — Conflict-Resolution Register

| Topic | Spec | BRD | Deck | Tasks | SSOT decision | Rationale |
| --- | --- | --- | --- | --- | --- | --- |
| Trader identity | Cell number | QR customer code, not phone | Trader code on every invoice | Cell number | Trader code (PK) + normalised phone (§4) | Owner decision; matches CSV history and informal traders |
| Primary data source | CSV of receipts | Manual capture → forms → API | Live invoices, WhatsApp, counter, QR, field | CSV | Branch CSV drop + WhatsApp bot + counter/QR/field capture, one contract (§5) | Deck flow; Spec contract |
| Timeline | 12 weeks | 30-day pilot | Test 5 Oct; 16 shops by 4 Nov; promo Nov–Dec | 14 days, go-live 9 Oct | Deck dates (§14) | Precedence rule |
| Phase 1 WhatsApp | Staff contact; broadcast for Lapsed | WhatsApp desk, API Month 2–3 | Automated bot, triggers on test day | Phase B | WhatsApp Business API bot in Phase 1 (§9) | Owner decision + Deck |
| Branch manager tooling | Action Queue, Trader 360 | Field agents | Field team task queue, counter alert | Upload page (RMG/branch admin) | Branch Manager interface: CSV drop + branch BI + ops (§10) | Owner decision |
| Segment taxonomy | 7 RFM segments | Loyalty tiers from RFM | Champions / Regulars / At-Risk / New (+ lapsed) | 7 segments | Deck 5 states; Spec's 7 kept as analyst sub-segments with a complete grid (§6) | Deck for names; Spec for method; gaps fixed |
| Frequency scoring | Quintiles | — | — | Quintiles | Fixed thresholds | Ties break quintiles |
| Lapse rule | 1.5× own gap; lapsed 3× / 90 days | 1.5× usual cycle | No order 14+ days | As Spec | 14 days OR 1.5× shrunk gap, whichever first; lapsed 3× / 90 days (§7.2) | Deck + Spec hybrid; BRD recall preference |
| Snapshot date | Latest receipt in all data | — | "Today" | Latest receipt | Per branch for CSV data; calendar date for live data (§11.5) | Late uploads |
| Walk-ins | Excluded from customer analytics | — | — | One anonymous customer per branch | Excluded | Anonymous customer would top rankings |
| Control group | 10% weekly random, At Risk + Needs Attention | Before/after | — | 10% weekly | Persistent 20% hash holdout, intent-to-treat, CI, hidden until powered (§11.7) | Contamination and power |
| Reconciliation | To CSV's own totals | — | — | To CSV | To ProDairy's independent totals (§5.4) | Self-reconciliation proves nothing |
| Stock / out-of-stock | Not supported | KPI | Stock-signal trigger, priority restocking | — | Phase 2 trigger; priority restocking as a Champion perk only (§2.3) | No stock feed |
| Loyalty points | — | Loyalty tier | Points in bot, perks | — | Tier in Phase 1; points ledger Phase 1b (Nov–Dec) | Deck promo timeline |
| "Live" dashboard | Refresh after each load | Weekly refresh | Live, updates nightly | — | Minutes for bot/counter data; on upload for CSV; nightly tier recompute (§11.1) | Honest to sources |
| Multi-tenancy | Single client | Client-partitioned from day one | — | client_id on rows | client_id on every row + RLS; no schema-per-tenant | Reuse without over-build |
| Scoring runtime | Python job | Scripts | — | Python job | dbt SQL in Phase 1; Python for Phase 2 models (§13) | One runtime, testable |
| lifetimes library | Suggested | — | — | Suggested | Not used (archived); pymc-marketing in Phase 2 | Maintenance |
| Web app folder | — | — | — | /app (README says web/) | web/ | Match README |
| BI tool for users | Web app; Metabase internal | Dashboard tool | Dashboard | Next.js | Next.js for all users; Metabase RMG-only | Users must write (CRM) |
| Document owners | — | Named RACI | — | — | Tinashe and Alvon | Owner decision |

# Appendix B — Glossary

| Term | Meaning |
| --- | --- |
| Trader | Any ProDairy customer buying for resale or household use (tuckshop, musika, vendor, small shop, wholesaler, household) |
| Trader code | System-issued unique identifier printed on the trader's QR card |
| Tier | Trader-facing level: New, Regular, Champion |
| Engine state | Internal risk state: At-Risk, Lapsed |
| Expected gap | A trader's typical days between purchases (shrunk median) |
| Overdue ratio | Days since last purchase ÷ expected gap |
| Holdout | Randomly assigned traders who receive no promotional prompts, used to measure lift |
| Template | A Meta-approved WhatsApp message format required for business-initiated messages |
| 24-hour window | Period after a trader's message in which free-form replies are allowed |
| BSP | WhatsApp Business Solution Provider |
| Bronze / Silver / Gold | Raw / cleaned / analytics-ready warehouse layers |
| RLS | Row-level security — database rules restricting each user to their branch |
| TDSP | Microsoft Team Data Science Process |
| CDPA | Zimbabwe Cyber and Data Protection Act (2021) |
| L0–L3 | Data maturity levels, from manual to fully automated capture |